MIDDLEWARE TEAM  ·  DELIVERY PLAN

From Here to Handover

What each of the 12 people does, day by day, until 3 September

| Written | 19 August 2026 |
| --- | --- |
| Handover | 3 September 2026 — 12 working days |
| Scope | Core emergency flow on the real database. Admin and auditor stay on mock data. |
| Status | Backend built and merged. Frontend not yet connected to it. |
| Supersedes | The original 8-block plan, which assumed the middleware still had to be written. |

# Contents

If this page is empty, click it and press F9 to build the list.

# 1.  Where the project actually stands

The original block plan assumed this team would spend three weeks writing a middleware layer. That layer now exists and is merged. The work that remains is almost entirely different from what the plan describes, so this document replaces it.

## Built and working

| Area | State |
| --- | --- |
| Authentication | JWT in httpOnly cookies, refresh rotation, session revocation, account lockout. Done. |
| Page guards | middleware.ts blocks unauthenticated access to /app/* by role. Done. |
| API pipeline | createHandler — rate limit, auth, roles, Zod validation, errors, audit. Done. |
| Request API | Create, list, detail, status, location, assign, notes, cancel. 15 endpoints. Done. |
| Routing | Nearest active organisation by distance, with a 150 km cap. Done. |
| Audit trail | Every meaningful action writes a row, server-side. Done. |

## Not started

| Area | State |
| --- | --- |
| The entire UI | All 22 pages still run on lib/mock-store.tsx and write to browser localStorage. Nothing the user does reaches the database. |
| Notifications API | No endpoint. The requester notifications page reads mock data. |
| Responders API | No endpoint. The dispatcher cannot list responders, so assignment cannot work. |
| Map | components/maps/live-response-map.tsx is an <svg> drawing, not a real map. |
| Demo data | No staff are linked to organisations, and there are no responders, teams or vehicles in the database. |

The single most important sentence in this document The backend is finished and the frontend has not been connected to any of it. Every remaining task is either wiring a page to an endpoint that already exists, or filling one of the small gaps listed above. Nobody needs to design anything new.

# 2.  Three blockers to clear before anything else

These are not warnings, they are certainties. If the first is not fixed, the dispatcher screen will be empty no matter how well the migration is done, and a day will be lost to debugging it.

### Blocker 1 — Staff are not linked to any organisation

In the deployed schema, a user's organisation comes from the organisation_members table, not from a column on users. No such rows exist. So auth.organisationId is null for every staff account, and listRequests() returns an empty array for dispatchers and responders.

Symptom: dispatcher signs in successfully, sees a completely empty queue, and everything looks broken.

Owner: Person 4, first thing.

### Blocker 2 — There are no responders, teams or vehicles

request_assignments references responder_profiles, responder_teams and vehicles by foreign key. Those tables are empty, so assignment is impossible — you cannot type a team name any more, the row must exist.

Owner: Person 4, same seed file.

### Blocker 3 — Nothing can list responders

Even with the data seeded, there is no GET endpoint returning the responders for an organisation, so the dispatcher's assign dropdown has nothing to populate from.

Owner: Person 10, first thing.

Do not start page migration until all three are done Persons 1, 3, 5, 6, 7 and 11 are all blocked behind them. That is why Phase 0 exists and why it is only three people wide. Everyone else spends those two days reading the code they are about to change.

# 3.  What becomes real, and what does not

Twelve working days is not enough to migrate 22 pages and build five endpoint groups. The decision taken is to make the core emergency loop genuinely real and leave the back-office screens on mock data, clearly labelled.

| Becomes real (9 pages) | Stays on mock data |
| --- | --- |
| Requester: submit, track, dashboard, history | Admin: users, organisations, settings, audit |
| Dispatcher: queue, request detail, dashboard | Auditor: incidents, audit |
| Responder: mission, history | Public landing page statistics |
| Notifications (requester) | Dispatcher: resources page |

Say this out loud in the demo A screen backed by mock data is only dishonest if you let people assume otherwise. Put a visible "Demo data" badge on every mock screen (Person 11) and state it plainly when demonstrating. Examiners respect a clearly drawn line far more than they respect a screen that quietly lies.

# 4.  The calendar

Twelve working days. Weekends are shown because a student team usually uses at least one of them — but nothing critical is scheduled on a weekend, so the plan survives if you do not.

| Dates | Phase | Who is working |
| --- | --- | --- |
| Wed 19 – Fri 21 Aug | Phase 0 — Unblock Seed data, missing endpoints, shared foundation | P4, P10, P9, P12, P2 (everyone else: read code, set up env) |
| Mon 24 – Fri 28 Aug | Phase 1 — Migration Wire the 9 core pages to the API | P1, P3, P5, P6, P7, P8, P11 (P2, P12 support and review) |
| Mon 31 Aug – Tue 1 Sep | Phase 2 — Map and integration Real map, end-to-end testing, mobile | P8, P11 build P3, P4, P5, P6 test |
| Wed 2 – Thu 3 Sep | Phase 3 — Documentation and handover Docs, evidence, rehearsal, release tag | P7, P8, P9, P10, P11, P12 |

Two fixed checkpoints Friday 21 Aug, end of day — a dispatcher signs in and sees a real request that a requester submitted from a browser. If this has not happened, Phase 1 cannot start on Monday and scope must be cut that afternoon, not the following week. Friday 28 Aug, end of day — the full loop works end to end on one machine. Phase 2 is testing and polish only. Anything not working by this point gets cut, not fixed.

# 5.  The pattern everyone follows

Read this section before starting your own task. It is the difference between nine people each inventing their own approach and nine people producing code that looks like one system.

## Do not rewrite pages. Adapt the data.

The components are good and they already work. They expect the shapes in lib/types.ts — EmergencyRequest, MockUser, Title-Case statuses. The API returns different shapes from types/index.ts — EmergencyRequestDetail, PublicUser, lowercase statuses.

Rather than editing every component, Person 2 builds one adapter that converts API shapes into the shapes the components already consume. Then migrating a page is a three-line change instead of a rewrite. This is the same trick that let the login change land without touching 18 files.

// BEFORE - reads browser localStorage const { db, loading, createRequest } = useMockStore(); const requests = db.requests; // AFTER - reads the database, same shape out const { requests, loading, refresh } = useRequests({ scope: "active" }); // The components below this line do not change at all.

## The three shared pieces

| Piece | Built by | What it does |
| --- | --- | --- |
| lib/middleware/client/api.ts | Already exists | Fetch wrapper. Unwraps the envelope, retries once on an expired token. Never call fetch directly. |
| lib/adapters/request-adapter.ts | Person 2 | Converts EmergencyRequestDetail to the EmergencyRequest shape components expect. |
| lib/hooks/use-requests.ts | Person 12 | useRequests(), useRequest(id), and the mutation helpers. Handles loading, errors and polling once, for everyone. |

Rules that keep this from turning into twelve different codebases Never call fetch directly in a page — use api.ts or a hook from use-requests.ts. Never store a Title-Case status. Convert with toDisplayStatus() at the moment of rendering. Every request submission needs a crypto.randomUUID() idempotency key. This is what stops a double-tap creating two emergencies. If a page needs data no endpoint provides, say so in the sync — do not query Supabase directly from a component.

# 6.  Person by person

Each person owns named files. If two people need the same file, one of them is wrong about their task — raise it in the morning sync rather than both editing it.

## Phase 0 — the five who unblock everyone (19–21 Aug)

## Person 4 — Database seed and backend liaison

| Phase | Phase 0 · Wed 19 – Thu 20 Aug |
| --- | --- |
| Depends on | Nothing. Start immediately. |
| Files owned | supabase/seeds/0002_demo_staff_and_resources.sql |

- Run the organisation seed that already exists: supabase/seeds/0001_responding_organisations_za.sql. Paste it into the Supabase SQL editor. Confirm it inserted 16 rows.

- Confirm the demo staff accounts exist in users — dispatcher, responder, admin, auditor — and note their UUIDs.

- Write a new seed inserting one organisation_members row per staff user, linking them to a seeded organisation with status = 'active'. This is the blocker.

- In the same file, insert two responder_teams and two vehicles for that organisation.

- Insert responder_profiles rows for the responder accounts — user_id is the primary key, organisation_id must be set, availability to 'available'.

- Verify by signing in as the dispatcher and calling GET /api/auth/me. The organisationId field must not be null.

- Ask the backend team the three open questions: are there RLS policies outside schema.sql, is bcrypt cost 10 correct, and who owns real organisation coordinates.

Done when Signing in as the dispatcher and calling GET /api/requests returns rows rather than an empty array, and GET /api/auth/me shows a non-null organisationId.

## Person 10 — Responders endpoint and test evidence

| Phase | Phase 0 · Wed 19 – Fri 21 Aug |
| --- | --- |
| Depends on | Person 4's seed, to test against. |
| Files owned | app/api/responders/route.ts |

- Build GET /api/responders using createHandler, with roles: ['dispatcher', 'admin'].

- Return every responder_profiles row for the caller's own organisation, joined to users for the name and to responder_teams and vehicles for labels.

- Scope it to ctx.user.organisationId inside the query, not filtered afterwards — a dispatcher must never see another organisation's crews.

- Support ?availability=available so the assign dropdown can show only free crews.

- Copy the shape of app/api/requests/route.ts. Do not invent a new response format.

- From 24 Aug onwards, switch to collecting test evidence: screenshots paired with the requestId from each response, which ties a screenshot to its audit row.

Done when A dispatcher can call GET /api/responders and receive their own organisation's crews, and an admin from another organisation receives a different list.

## Person 9 — Notifications API

| Phase | Phase 0 · Wed 19 – Fri 21 Aug |
| --- | --- |
| Depends on | Nothing. Start immediately. |
| Files owned | app/api/notifications/route.ts, app/api/notifications/[id]/route.ts |

- Build GET /api/notifications returning the signed-in user's own rows from the notifications table, newest first, with a limit and offset query schema.

- Restrict to recipient_user_id = ctx.user.userId inside the query. A notification is personal data — nobody sees anyone else's.

- Build PATCH /api/notifications/[id] that sets read_at. Return 404, not 403, if the row belongs to someone else, so the endpoint does not confirm it exists.

- Add a createNotification() helper in lib/middleware/server/ and call it from changeStatus() in requests-service.ts, so a status change tells the requester.

- A failed notification insert must never fail the status change that triggered it. Log and swallow, as writeAudit does.

- From 2 Sep: write the deferred-features section of the handover — push, SMS, email verification, password reset.

Done when A requester sees a notification appear after a dispatcher changes their request status, and cannot see another requester's notifications.

## Person 12 — Shared data hooks

| Phase | Phase 0 · Wed 19 – Fri 21 Aug |
| --- | --- |
| Depends on | Nothing. This is what the others build on. |
| Files owned | lib/hooks/use-requests.ts |

- Build useRequests({ scope, status, search }) returning { requests, total, loading, error, refresh }, calling apiGet from lib/middleware/client/api.ts.

- Build useRequest(id, { pollMs }) for the detail and tracking pages. When pollMs is set, re-fetch on that interval and clear the timer on unmount.

- Default the poll interval from NEXT_PUBLIC_POLL_INTERVAL_MS, which already exists in .env.example.

- Build mutation helpers: updateStatus, assignResponder, addNote, cancelRequest. Each calls the endpoint then triggers refresh().

- Surface errors as the ApiClientError message. Do not swallow them into a generic string — the server writes good messages, use them.

- Write a short usage example at the top of the file. Seven people will copy it; make the copy worth making.

- From 2 Sep: review every document for completeness and confirm every endpoint has been exercised at least once.

Done when Two different pages use the hooks with no duplicated fetching, loading or error-handling code between them.

## Person 2 — The adapter, and the shared contract

| Phase | Phase 0 · Wed 19 – Fri 21 Aug |
| --- | --- |
| Depends on | Nothing. Person 12 depends on you. |
| Files owned | lib/adapters/request-adapter.ts |

- Write toUiRequest(detail: EmergencyRequestDetail): EmergencyRequest converting the API shape into the shape in lib/types.ts that the components already consume.

- Map the fields that differ: reference to the displayed id, location from the nested object, statusHistory from history, operationalNotes from the notes array.

- Convert status with toDisplayStatus() from lib/middleware/status.ts. Never hand-write the Title-Case strings.

- Handle a null location — a manual address with no coordinates is real and must not crash a page.

- Walk the frontend and backend teams through the field renames in section 2 of the integration plan. The renames are what will confuse people, not the concepts.

- From 24 Aug: you are the reviewer. Read every migration pull request before it merges.

Done when app/app/dispatcher/requests/[id]/page.tsx renders a request that came from the API, with no changes to any component below the page.

## Phase 1 — the seven who migrate the UI (24–28 Aug)

Everyone here depends on Phase 0 finishing. Use 19–21 August to read the page you are about to change, run the app, and sign in as the role you are building for.

## Person 1 — Request submission — the biggest single file

| Phase | Phase 1 · Mon 24 – Thu 27 Aug |
| --- | --- |
| Depends on | Persons 2, 12, 4. |
| Files owned | app/app/requester/new/page.tsx (31 KB) |

- Replace createRequest from useMockStore with apiPost('/api/requests', ...). This is the single most important change in the project — it is the moment real emergencies start reaching the database.

- Generate idempotencyKey with crypto.randomUUID() once when the form mounts, not on submit. Regenerating on submit defeats the entire duplicate-prevention mechanism.

- Map the form fields to the API: category and severity must be lowercase, callbackNumber is required, locationMethod is gps, manual or map_pin.

- On a validation failure the API returns error.details keyed by field name. Render those under the matching inputs rather than as one banner.

- On success the response includes organisationName — the organisation the request was routed to. Show it on the confirmation screen. That is the routing being visibly real.

- Keep the existing multi-step form and styling. This is a data-layer change, not a redesign.

- Test a double submit with the same key. It must return the same request, not create a second one.

Done when A requester submits from the browser, the row appears in Supabase with a reference code and a routed organisation, and submitting twice creates one request.

## Person 3 — Requester tracking and dashboard

| Phase | Phase 1 · Mon 24 – Thu 27 Aug |
| --- | --- |
| Depends on | Persons 2, 12; Person 1 for a request to track. |
| Files owned | app/app/requester/track/[id]/page.tsx, app/app/requester/page.tsx |

- Replace useMockStore with useRequest(id, { pollMs }) on the tracking page so status changes made by a dispatcher appear without a manual refresh.

- Replace the dashboard's data source with useRequests({ scope: 'mine' }).

- Render the status timeline from the API history array. It already records who changed each status and when.

- Wire the cancel button to POST /api/requests/[id]/cancel. Remember the rule: before assignment a requester cancels outright, after assignment they request cancellation and staff confirm.

- Show statusExplanation() from lib/middleware/status.ts rather than writing your own wording. It is deliberately careful never to imply help is on the way before it is.

- From 31 Aug: own the end-to-end test — register, submit, dispatch, assign, en route, arrived, close — and test every endpoint with an invalid token.

Done when A requester watches their status change live while a dispatcher moves it on another machine, without either of them refreshing.

## Person 5 — Dispatcher queue and dashboard

| Phase | Phase 1 · Mon 24 – Wed 26 Aug |
| --- | --- |
| Depends on | Persons 2, 12, 4. |
| Files owned | app/app/dispatcher/requests/page.tsx, app/app/dispatcher/page.tsx |

- Replace useMockStore with useRequests({ scope }), wiring the existing new / active / completed tabs to scope=new, scope=active and scope=completed.

- Poll the queue. A dispatcher must not have to refresh to see a new emergency arrive.

- Show the routed organisation and, where available, the distance. An unrouted request must be visibly flagged — those are the ones needing human triage.

- Compute the dashboard counts from the API total rather than counting a client-side array, which is only ever the current page.

- From 28 Aug: test the status transition rules. Try closed to assigned and confirm a 409 STATUS_TRANSITION_INVALID. Test rate limiting and confirm CORS is same-origin only.

Done when A request submitted on one machine appears in the dispatcher queue on another within one poll interval, with its routed organisation shown.

## Person 6 — Dispatcher request detail — assign, advance, note, reject

| Phase | Phase 1 · Mon 24 – Fri 28 Aug |
| --- | --- |
| Depends on | Persons 2, 12, 4, and Person 10's responders endpoint. |
| Files owned | app/app/dispatcher/requests/[id]/page.tsx |

- This page has four actions behind sheets. Wire each to its endpoint: assign to POST /api/requests/[id]/assignments, advance to PATCH /api/requests/[id]/status, note to POST /api/requests/[id]/notes, reject to PATCH status with { status: "rejected", reason }.

- Populate the assign dropdown from Person 10's GET /api/responders. It passes real UUIDs now — responderUserId, teamId, vehicleId — not the free-text labels the mock used.

- Send expectedStatus with every status change. If two dispatchers act at once the second gets a 409 instead of silently overwriting the first.

- Show the allowed next statuses using nextStatusesFor(current, role) rather than hardcoding a sequence. The server enforces the same rules; if the button is not offered, the call would have failed anyway.

- Reject requires a reason. Enforce it in the UI as well as the API so the operator is told before the round trip, not after.

- The reroute action has no endpoint. Either drop it for this release or raise it on 24 Aug — do not build a silent no-op button.

Done when A dispatcher assigns a real responder to a real request, the assignment row appears in Supabase, and the requester's tracking page reflects it.

## Person 7 — Responder mission view

| Phase | Phase 1 · Mon 24 – Wed 26 Aug |
| --- | --- |
| Depends on | Persons 2, 12, 4; Person 6 for an assignment to act on. |
| Files owned | app/app/responder/page.tsx, app/app/responder/history/page.tsx |

- Replace useMockStore with useRequests({ scope: 'active' }). A responder sees their organisation's requests; ownership is applied in the query, so no client-side filtering is needed.

- Wire the accept and status buttons to PATCH /api/requests/[id]/status. A responder may set en_route and arrived but not closed — that is a dispatcher action and the server will refuse it.

- Add a route link using routeLinkUrl() from lib/middleware/geo.ts, which opens the responder's own maps application with the incident as the destination.

- History uses useRequests({ scope: 'completed' }).

- From 31 Aug: run the whole flow on a physical phone over ngrok. Set ALLOW_INSECURE_COOKIES=1 and check GET /api/health first — if that fails nothing else will work.

- From 2 Sep: write the middleware setup guide and document every endpoint with a worked example.

Done when A responder accepts an assignment, sets en route then arrived, and the requester sees each change on their tracking page.

## Person 8 — Location capture, then the real map

| Phase | Phase 1 and 2 · Mon 24 Aug – Tue 1 Sep |
| --- | --- |
| Depends on | Person 1, whose form captures the position. |
| Files owned | app/app/requester/new/page.tsx (location step), components/maps/live-response-map.tsx |

- The form already calls navigator.geolocation.getCurrentPosition. Send what it captures to PUT /api/requests/[id]/location — currently the coordinates are captured and then discarded.

- Wire the denied-permission path to the same endpoint with locationMethod: "manual" and an addressText. Both paths are real and both must work.

- Test the three cases explicitly: permission granted, permission denied, and an invalid coordinate such as latitude 91, which must return a 422.

- Never log coordinates. The audit records that a location arrived, never where. That is deliberate and must stay that way.

- From 31 Aug: replace the <svg> mock map with a real one using osmEmbedUrl() from lib/middleware/geo.ts — a key-free OpenStreetMap embed. The Content-Security-Policy in middleware.ts already permits it.

- From 2 Sep: document every environment variable and write the known-limitations list.

Done when A request carries the position the browser actually reported, a denied-permission request still works via a typed address, and the map shows real geography.

## Person 11 — Notifications page, demo labelling, then rehearsal

| Phase | Phase 1 and 3 · Mon 24 Aug – Thu 3 Sep |
| --- | --- |
| Depends on | Person 9's notifications endpoint. |
| Files owned | app/app/requester/notifications/page.tsx, plus a shared demo badge |

- Wire the notifications page to Person 9's GET /api/notifications, and mark-as-read to the PATCH endpoint.

- Build one small <DemoDataBadge /> component and place it on every screen still backed by mock data — admin, auditor, dispatcher resources, the landing page statistics.

- That badge is what makes the split scope honest rather than misleading. It is a small component with a large amount of integrity attached to it.

- From 31 Aug: you are the backup for anyone who is behind. Ask in the Monday sync who is at risk before choosing.

- From 2 Sep: rehearse the demonstration end to end at least three times, on the machine you will actually present from.

- Write the handover document for whoever picks this up next: what works, what is mocked, what you would do first with another two weeks.

Done when Notifications come from the database, every mock screen is visibly labelled, and the demo has been rehearsed on the presenting machine.

# 7.  Definition of done

The project is finished when this sequence works on one machine, in front of an audience, without anyone touching a database console. Rehearse exactly this.

- A new requester registers. The account is created and they are signed in automatically.

- They submit an emergency. The browser captures GPS; they see a reference code and the organisation it was routed to.

- The row exists in Supabase — show it, with reference_code, routed_organisation_id and a request_locations row.

- On a second machine, a dispatcher signs in and the request is already in the queue.

- The dispatcher assigns a real responder. The requester's screen updates without a refresh.

- On a phone, the responder accepts, sets en route, then arrived. The requester watches each change.

- The dispatcher closes the request. It moves to completed on all three screens.

- An auditor opens the audit trail and finds every one of those actions, with who did it and when.

- Sign out. Try to open /app/dispatcher directly. You are redirected to the sign-in page.

The last step is the one to practise Showing that an unauthenticated visitor cannot reach a protected page is the clearest 10 seconds of evidence you have that this is real software rather than a set of screens. Do not leave it out because you ran short of time.

# 8.  What to cut if you fall behind

Decide these in the sync, in this order, and write down what you cut. An examiner asking "why is there no map" wants to hear a decision, not an excuse.

| Cut first | Then | Never cut |
| --- | --- | --- |
| The real map — keep the SVG mock | Notifications — the flow works without them | The requester → dispatcher → responder loop |
| Responder history and profile | Requester history | Authentication and the page guards |
| The reroute action | Dispatcher activity feed | The audit trail |
| Distance display on the queue | Mark-as-read | Documentation and the handover |

## Standing risks

- Phase 0 slipping. Seven people are blocked behind three. If Person 4 is stuck on Wednesday, everyone should know on Wednesday, not Friday.

- Everyone editing the same file. Each person owns named files. Two people in dispatcher/requests/[id]/page.tsx will produce a merge conflict in a 7 KB single-line file, which is close to unresolvable.

- Rate limiting during the demo. Ten submissions per user per minute. Rehearsing repeatedly will trip it. Set RATE_LIMIT_ENABLED=0 while rehearsing and turn it back on before presenting.

- The service-role key. Still the placeholder-era key in .env.local. Rotate it before the repository is shared with anyone outside the team.

- Nobody has run this on a phone yet. Person 7 should do that in week one, not on 1 September. A layout that breaks on a real device is a bad thing to discover the day before handover.

## Sync meetings

Person 1 runs Monday and Friday. Person 12 takes the minutes and sends them to everyone. Three questions each time, and keep it to fifteen minutes: what did you finish, what are you blocked on, and is anyone about to touch a file you own.